## Sprint Backlog
Sprint Backlog
|  |  |  | IDEAL PATH: | 54 | [8 empty] | 0
ID | Story ID | Task Description | Assigned To | Status | Estimate | 2015-10-26 | 2015-10-28 | 2015-10-30 | 2015-11-02 | 2015-11-04 | 2015-11-06 | 2015-11-09 | 2015-11-11 | 2015-11-13 | Remaining
1 | 21 | Create framework for a player's inventory. | Benjamin Priyadamkol | Not Started | 6 | [9 empty] | 6
2 | 21 | Allow players to pick up objects by tapping on them. | Benjamin Priyadamkol | Not Started | 4 | [9 empty] | 4
3 | 17 | Allow players to open the cage door using the skeleton key. | Benjamin Priyadamkol | Not Started | 4 | [9 empty] | 4
4 | 17 | Functionality for ending the level when player steps into the cage door. | Rajib Saha | Not Started | 4 | [9 empty] | 4
5 | 22 | Display health on screen. | Rajib Saha | Not Started | 2 | [9 empty] | 2
6 | 22 | Create health component for characters. | Rajib Saha | Not Started | 8 | [9 empty] | 8
| 18 | Render traps in level. | Aaron Murphy | Not Started | 2 | [9 empty] | 2
7 | 18 | Implement visual effects for traps. | Aaron Murphy | Not Started | 6 | [9 empty] | 6
8 | 18 | Functionality for activiting traps. | Aaron Murphy | Not Started | 6 | [9 empty] | 6
9 | 19 | Render enemies in the level. | Byron Roby | Not Started | 2 | [9 empty] | 2
10 | 19 | Animation for enemies. | Byron Roby | Not Started | 4 | [9 empty] | 4
11 | 19 | Functionality for moving enemies towards players. | Byron Roby | Not Started | 6 | [9 empty] | 6
|  |  |  | WORK REMAINING: | 54 | #N/A | #N/A | #N/A | #N/A |  |  |  |  | #N/A | 54
This shape represents a table slicer. Table slicers are supported in Excel 2013 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel 2013 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel 2013 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.